## Sheet1
Sl No | Module | Sub Module - 1 | Sub Module - 2 | Developer | Tester | Time Required | Start date | End date | Remark
Project Analysis
Internal Team Discussion
| Project set up |  |  | Pravat
| UI Set up |  |  | Pravat
| Super Admin | Login | User Name | Bipin
|  |  | Password | Bipin
|  | User Creation | Company Create | Krishna
|  | Domain registration |  | Krishna
|  | PIN Code | Maping | Bipin
|  | Role creation |  | Krishna
| Warehouse | Warehouse - UI, Backend |  | Preetam |  | 1 day | 2023-11-25 | 2023-11-25
|  | Sector - UI, Back end |  | Lalu |  | .5 day | 2023-11-25 | 2023-11-25
|  | Category - UI, Back end |  | Lalu |  | 1 day | 2023-11-27 | 2023-11-27
|  | Items - UI, Back end |  | Preetam |  | 3 days | 2023-11-27 | 2023-11-29
|  |  | Manufacturing Opertaion Managemet (MOM) | Lalu |  | 2 days | 2023-11-28 | 2023-11-29
|  | Unit - UI, Back end |  | Preetam |  | 1 day | 2023-11-30 | 2023-11-30
|  | Unit of Measurement - UI, Back end |  | Preetam |  | 1 day | 2023-12-01 | 2023-12-01
|  | Employee create - UI, Back end |  | Bipin |  | 1 day | 2023-11-25 | 2023-11-25
|  | Employee on Boarding - UI, Back end |  | Bipin |  | 2 days | 2023-11-27 | 2023-11-28
|  | Vechile reg. - UI, Back end |  | Trinath |  | 1 day | 2023-11-27 | 2023-11-27
|  | Vendor / Party / Seller | Vendor create | Trinath |  | 1 day | 2023-11-28 | 2023-11-28
|  | Delivery Partner - UI, Back end |  | Bipin |  | 2 days
|  | Stock management | Damage product entry | Lalu
|  | Sales executive creation - UI, Back end |  | Preetam
|  |  | My Acc | Preetam
|  |  | My order | Preetam
|  |  | Dashboard | Preetam
|  |  | Sales & Purchase Order tracking | Preetam
| Sales | Sales team create |  | Lalu
|  |  | Sales team assign | Lalu
|  | Gross margin |  | Lalu
| Seller - Web | Seller project Setup |  | Harekrishna
|  | Seller reg. | Sign Up | Preetam
|  |  | Sign In | Preetam
|  | Profile | Edit | Trinath
|  |  | My Acc | Trinath
|  |  | My order | Trinath
|  | Product entry |  | Bipin
|  | Dashboard | Graphical | Bipin
|  |  | Analytical | Bipin
|  | Sales order tracking | Business logic | Bipin
|  |  | Service | Lalu
| Seller - mobile | Figma |  | Client / Rajashree
|  | Seller project Setup |  | Padma
|  | Seller reg. | Sign Up - API Integration | Rakesh
|  |  | Sign In - API Integration | Rakesh
|  | Profile | Edit - API Integration | Rakesh
|  |  | My Acc - API Integration | Rakesh
|  |  | My order - API Integration | Rakesh
|  | Product entry - API Integration |  | Rakesh
|  | Dashboard | Graphical - API Integration | KD
|  |  | Analytical - API Integration | KD
|  | Sales order tracking | Business logic - API Integration | Rakesh
|  |  | Service - API Integration | Rakesh |  |  |  | 2023-12-09